## Sheet1
SrNo. | Points | Date | Responsibility | Status | Remarks
AISIN Visit 18-02-21
1 | LAN connection OK with all door locking 2 lines and 5 handle lines confirm by AISIN IT Team rest all pending. | 18-02-2021 | AISIN | Pending | Closed
2 | We have successfully tested with our Printer Application(AEP) on handle Line(AS0104) from Printing to Dispatch. | 18-02-2021 | SATO | Done
3 | Now part kanban barcode has changed,it will be in 3 format but position will be same in two format (45,46)shared to kailash san. | 18-02-2021 | AISIN | Pending | Status need to confirm by ASIAN Team
4 | Kens scanner still not working. | 18-02-2021 | AISIN | Pending | Closed
5 | PC will be of user front on all door locking line where our pc application run. | 18-02-2021 | AISIN | Pending
AISIN Visit: 22/23-02-21
1 | Location barcode printing done along with Vikash San. | 22-02-2021 | SATO | Done
2 | Process wise report implemented | 22-02-2021 | SATO | Done
3 | Lan connection is Ok for all lines tested with AISIN IT Team | 23-02-2021 | SATO | Done
4 | We have successfully tested our application with Kans scaner along with Vikas San | 23-02-2021 | SATO | Done
5 | PC will be of user front on all door locking line where our pc application run. | 23-02-2021 | AISIN | Done
AISIN Visit : 01-03-21
1 | Setup of 11 printers has been done at their required location | 01-03-2021 | SATO | Done
2 | Label & ribbon also has been installed in all the printers. | 01-03-2021 | SATO | Done
3 | Power supply is required at all the location for further application installation | 01-03-2021 | AISIN | Done
AISIN Visit : 08-03-21
1 | Only for one printer we got the power supply, AEP has been installed in that printer | 08-03-2021 | SATO | Done
2 | PC application installation also done in 3 system of users. | 08-03-2021 | SATO | Done
3 | 4 HHsT devices also have been configured. | 08-03-2021 | SATO | Done
4 | Power supply is pending for remaining 10 printers | 08-03-2021 | AISIN | Done | As per kailash San, tomorrow it will be completed.
AISIN Visit : 25-03-21
1 | We have successfully tested the AEP application with our Printer at 8 locations | 25-03-2021 | SATO | Done
2 | We have successfully tested the PC application with our Printer at 5 locations. | 25-03-2021 | SATO | Done
3 | We have configured the device application in 4 HHsT devices. | 25-03-2021 | SATO | Done
4 | Need usb cable for printer | 25-03-2021 | SATO | Pending | SATO Provided in Next visit
5 | In 2 location printer power and lan setup pending from AISIN side | 25-03-2021 | AISIN | Pending | As per kailash San, tomorrow it will be completed.
6 | Network connection issue at small location | 25-03-2021 | AISIN | Done | As per kailash San, tomorrow it will be completed.
AISIN Visit : 05-04-21
1 | We have successfully tested the AEP application with our Printer at 10 locations | 05-04-2021 | SATO | Done
2 | We have successfully tested the PC application with our Printer at 5 locations. | 05-04-2021 | SATO | Done
3 | We have provided AEP application and printer configuration training to AISIN line engineers (Vipul and Ashima). | 05-04-2021 | SATO | Done
4 | Need 4 usb cable for printer | 05-04-2021 | SATO | Pending | SATO Provided in Next visit
5 | Kans scanner setup pending at 4 door lock location | 05-04-2021 | AISIN | Pending | As per kailash San, tomorrow it will be completed.