## To Do Next
SrNo. | To Do Next Plan | Resposibilty | Tentative Expected Date | Action
1 | LAN Connection at every lines | ASIN | Disscused with kailash San Date will be provided by Monday | We will required LAN connection also at industrial PC lines ,if using with wifi data travel on the server can be slow confirmed by SATO.
2 | KEN Scanner data should be show on the PC Cursor point. | ASIN | Disscused with kailash San Date will be provided by Monday
3 | Now We have fixed two type internal Kanban barcode format (with 0 and without 0) . | ASIN | Disscused with kailash San Date will be provided by Monday | Need to check all part and rectify if any.
4 | Process Wise Report | SATO | 2021-01-19
5 | Current Honda Domestic Customer Kanban does not have Part barcode so we are unable to validate at Dispatch time also currently not given any provison in our application. | ASIN | Disscused with kailash San Date will be provided by Next week | Need to check the feasibility as per our scope if they can do any changes.
6 | Stationary (Label and Ribbon) | SATO | In Next visit | Ready,We will brought in next visit or provide through courier service.
7 | AEP Application (Printer Application and Device Application) testing is pending because of LAN Connection is not available on the All Lines. | SATO/ASIN | Disscused with kailash San Date will be provided by Next week | When LAN connection will be availbale then we can test at Line.
8 | Location Barcode Labeling with current stock | ASIN | Disscused with kailash San Date will be provided by Next week
9 | Production PC should be at front side so that user able to see running opreation clearly. | ASIN | Disscused with kailash San Date will be provided by Next week

## Completed Task
SrNo. | Points | Testing Date | Status | Remarks
1 | At production line, First cycle, using pc application we have tested cycle from Production bin printing to dispatch with customer Kanban(for Toyota only). | 2021-01-14 | Done | Along with kailash san
2 | Next Cycle we have tested, Service Part and Fraction at production line to dispatch and direct dispatch also. | 15,16-01-2021 | Done | Along with kailash san
3 | Production Line part rejection at running line scenario and Last part after completed bin. | 2021-01-15 | Done | Along with kailash san
4 | Fraction bin wise rejection and part wise rejection and normal rejection with bin wise and part wise both. | 2021-01-15 | Done | Along with kailash san
5 | Direct dispatch loading list,Truck Reopen and Truck out. | 15,16-01-2021 | Done | Along with kailash san